## Slide 1: PRIORITY AREA 10 ROADMAP TO ACTIONS Working Group 1 – Institutional Capacity Working Group 4 – Financing
2nd Steering Group Meeting
29th and 30th March 2012

## Slide 2: Roadmap for the Action: Working Group 1
WORKING GROUP 1 (INSTITUTIONAL CAPACITY) - OVERVIEW
1 action allocated to the WG 1:
Action: ‘To Combat Institutional Capacity and Public Service Related Problems in the Danube Region’.
At least 8 projects allocated to the action. Many projects have institutional capacity component.
Next steps, activities and tasks of the WG members have already been as a meeting follow-up.

## Slide 3: Roadmap for the action: Working Group 1 – Institutional Capacity
Milestone N°1 (operational steps) | Main Objective | Results | Responsibility | Deadline | Projects allocated to the Action
Identify stakeholders | One of the ways to step up institutional capacity is also through training, knowledge sharing and exchanging of experiences typically carried out by public administration and specialized training institutions. However, there are different structures, approaches and levels of specialization in the region. Additional stakeholders will be identified utilizing networks, desk research and WG1 meetings. | Comprehensive list of public administration and other specialized institutions and others from Danube region countries. | Working group members | March 9, 2012 | 1. Academy for Exchange in Administration in the Danube Region (City of Passau, DE).
Action ‘To Combat Institutional Capacity and Public Service Related Problems
in the Danube Region’

## Slide 4: Roadmap for the action: Working Group 1 – Institutional Capacity
Milestone N°2 (operational steps) | Main Objective | Results | Responsibility | Deadline | Projects allocated to the Action
Identify areas of institutional capacity needs / gaps in the Danube region | Due to different economic, social and other factors, the Danube region countries have achieved very different levels of institutional capacity and therefore also needs. Through group work and written input by WG1 members, areas where particular attention in the institutional capacity will be recognized on both levels - capacity needs of institutions providing training and capacity needs of the trainees. | Indicative list of institutional capacity gaps in the Danube region | Working group members | March 9, 2012 | 2. Procurement (BBG, AT). 3. IPA Workshops (CEF, SI). 4. BCPDI: Fiscal Impact Assessment of Structural Reforms (CEF, SI). 5. BCPDI: Strategic Planning and Budgeting (CEF, SI). 6. First alignment with the transport aquis (Min. of Transport, DE, AT, RS) 7. Harmonization with Aquis Communitaire (Min. of Infrastructure and Energy FR, LIT, RS) 8. TA to support the Min. of Infrastructure and Energy (RS) Output: {number tbc} of participants trained and inst. capacity improved.
Action ‘To Combat Institutional Capacity and Public Service Related Problems
in the Danube Region’

## Slide 5: Roadmap for the action: Working Group 1 – Institutional Capacity
Milestone N°3 (operational steps) | Main Objective | Results | Responsibility | Deadline | Projects allocated to the Action
Present / publish paper “Institutional Capacity Development Through Implementation of the EUSDR” at NISPAcee Annual Conference | NISPAcee, a network of institutes and public administration schools in the Central and Eastern Europe put on a call for papers to be published and presented at the annual conference. PAC submitted an outline of the paper to be presented within the working group on internationalization and networking of PA studies. The concept paper was approved in Dec. 2011 to be presented at NISPAcee annual conference (Ohrid, May 23 - 26, 2012). Based on inputs provided by WG1 members at the February WG1 meeting, their written input and research a paper will be prepared and presented. | Increased visibility of the EUSDR and institutional capacity efforts in the region. | Working group members PAC10 Coordinator (PAC, CEF) | For WG members March 9, 2012 For PAC April 10, 2012 | 
Action ‘To Combat Institutional Capacity and Public Service Related Problems
in the Danube Region’

## Slide 6: Roadmap for the action: Working Group 1 – Institutional Capacity
Milestone N°4 (operational steps) | Main Objective | Results | Responsibility | Deadline | Projects allocated to the Action
Event / workshop “From project design to implementation” Title of the event tbc. (Note: the event complements the PA10 WG4 on Financing objectives and action plan) | Design and execute training for EUSDR target group on how to develop a project from idea to implementation. Lack of experience in project cycle management and inefficient use of financial resources contribute to poor project preparation and lackluster implementation. It is also important that stakeholders are aware of funding opportunities and understand different funding requirements and principles. This is in particular relevant for EUSDR projects as they should be transnational and as such could be funded by different financial sources - national, Structural and/or Cohesion fund, IPA, ENPI, European Investment Bank and other IFIs as well as through Western Balkan Investment Framework (WBIF). For non-EU member states participation in EUSDR on project level means also the possibility of gaining practical experience on “how to run an EU project” in line with the EU acquis. Gaining practical experience is an important element of institutional building and value added for the EU integration process. | 40-50 participants Increased capacity in PCM, EU funds management. | PAC10 European Commission (DG Regio) | July 6, 2012 | 
Action ‘To Combat Institutional Capacity and Public Service Related Problems
in the Danube Region’

## Slide 7: Roadmap for the action: Working Group 1 – Institutional Capacity
Milestone N°5 (operational steps) | Main Objective | Results | Responsibility | Deadline | Projects allocated to the Action
Identify existing training programs and other areas of institutional capacity development that could be shared or mutually developed by training institutions in the Danube region | Though WG discussion, exchange of experiences and capacity needs, the stakeholders will identify existing links and see if synergies exist. The stakeholders will build on best practices and examine if existing training programs designed on a national level could be applicable on the supranational level within the Danube region. Apart from training, other areas of mutual cooperation in institutional capacity development could be identified and developed. | Training programs and other areas of institutional capacity development shared. | Working group members | End 2013 | To be developed.
Action ‘To Combat Institutional Capacity and Public Service Related Problems
in the Danube Region’

## Slide 8: Roadmap for the action: Working Group 1 – Institutional Capacity
Milestone N°6 (operational steps) | Main Objective | Results | Responsibility | Deadline | Projects allocated to the Action
Identify new training programs and other areas of institutional capacity development that could be mutually developed by training institutions in the Danube region | Though WG discussion, exchange of experiences and capacity needs, the stakeholders will identify existing links and see if synergies and potential to mutually develop new training programs exist. Apart from training, other areas of mutual cooperation could be identified and developed. | New areas of cooperation focused of institutional capacity | Working group members | End 2013 | To be developed.
Action ‘To Combat Institutional Capacity and Public Service Related Problems
in the Danube Region’

## Slide 9: Roadmap for the action: Working Group 1 – Institutional Capacity
Milestone N°7 (operational steps) | Main Objective | Results | Responsibility | Deadline | Projects allocated to the Action
Identify / find funding | Public administration training institutions face a number of difficulties in securing EU funding for EU-related projects (lengthy procedures, lack of experience, eligibility, combining resources when it comes to beneficiaries from EU MS, potential and candidate, neighborhood countries as is the case for the Danube region and others). Each country or region to identify / find the financing from their national or regional budgets (op. programes) as well as the ERDF or Cohesion Fund and other financing sources. | Improved access to EU funding. Funding for new training program(s) to step up capacity designed for the Danube regions | Working group members. | End 2013 | To be developed - depending of results of milestone 5 and 6.
Action ‘To Combat Institutional Capacity and Public Service Related Problems
in the Danube Region’

## Slide 10: Roadmap for the Action: Working Group 4
WORKING GROUP 4 (FINANCING) - OVERVIEW
1 action allocated to the WG 4:
  Action: ‘To Review Bottlenecks Relating to the Low Absorption of EU Funds and to Ensure Better Coordination of Funding’
Cross-cutting WG, only a couple of projects allocated to the action (also allocated to WG1 – Institutional Capacity).
Next steps, activities and tasks of the WG members to be done until next meeting .

## Slide 11: Roadmap for the action: Working Group 4 – Financing
Milestone N°1 (operational steps) | Main Objective | Results | Responsibility | Deadline | Projects / cross-reference to other EUSDR initiatives
Review bottlenecks in EU funds absorption | There is a large variation among EU member countries, candidates, potential candidates, and European neighborhood policy countries in the absorption of EU funds which in overall is disappointing. Important constraints in EU funds absorption are a consequence of insufficient administrative capacity and inadequate knowledge of how to prepare and implements projects. There are already initiatives in place to improve the capacity for absorbing EU and other development funds which are not available to all countries from the Danube region. This is also reflected in the report “Analysis of needs for financial instruments in the EUSDR” (Metis, nov. 2011). Through desk research, WG4 meeting discussions, written input by WG4 members financial, administrative and other bottlenecks faced by the Danube region countries will be identified and review. | A report with an overview on financial, administrative and other bottlenecks related to absorption of EU funds for the Danube region countries. | Working group members and PAC | End 2012 | Study / report: “Analysis of needs for financial instruments in the EUSDR”, done by Metis, November 2011.
Action ‘To Review Bottlenecks Relating to the Low Absorption of EU Funds
And to Ensure Better Coordination of Funding’

## Slide 12: Roadmap for the action: Working Group 4 – Financing
Milestone N°2( operational steps) | Main Objective | Results | Responsibility | Deadline | Projects allocated to the Action
Event / workshop “From project design to implementation” Title of the event tbc. (Note: the event complements the PA10 WG4 on Financing objectives and action plan) | Design and execute training for EUSDR target group on how to develop a project from idea to implementation. Lack of experience in project cycle management and inefficient use of financial resources contribute to poor project preparation and lackluster implementation. It is also important that stakeholders are aware of funding opportunities and understand different funding requirements and principles. This is in particular relevant for EUSDR projects as they should be transnational and as such could be funded by different financial sources - national, Structural and/or Cohesion fund, IPA, ENPI, European Investment Bank and other IFIs as well as through Western Balkan Investment Framework (WBIF). For non-EU member states participation in EUSDR on project level means also the possibility of gaining practical experience on “how to run an EU project” in line with the EU acquis. Gaining practical experience is an important element of institutional building and value added for the EU integration process. | 40-50 participants Increased capacity in PCM, EU funds management. | PAC10 European Commission (DG Regio) | July 6, 2012 | 
Action ‘To Review Bottlenecks Relating to the Low Absorption of EU Funds
And to Ensure Better Coordination of Funding’

## Slide 13: Roadmap for the action: Working Group 4 – Financing
Milestone N°3 (operational steps) | Main Objective | Results | Responsibility | Deadline | Projects / cross-reference to other EUSDR initiatives
Identify ways to ensure better coordination of funding | Though WG4 discussion and exchange of experiences the need to build institutional capacity leading to better management and use of EU funds was recognized. | Recommendations, best practice examples | Working group members | End 2013 | PA10 flagship project: Danube Implementation Facility Projects: 1. IPA Workshops (CEF, SI). 2. Procurement (Austrian Federal Procurement agency – BBG). Output: {number tbc} of participants trained on IPA funds, public financial management and public procurement.
Action ‘To Review Bottlenecks Relating to the Low Absorption of EU Funds
And to Ensure Better Coordination of Funding’

## Slide 14: Roadmap for the action: Working Group 4 – Financing
Milestone N°3 (operational steps) | Main Objective | Results | Responsibility | Deadline | Projects / cross-reference to other EUSDR initiatives
New programming period (2014 – 2020): explore if PA10 WG4 can act as a platform for recommendations to the EC by the EUSDR, especially non-EU stakeholders | The EUSDR should be taken into account when planning and implementing the next programming period. Recent proposals of the European Commission for the 2014 – 2020 programming period would be discussed and its implications to EUSDR interpreted together with solutions reflecting the macro-regional (EUSDR) focus. As many countries of the EUSDR region (EU candidate, potential candidate and neighborhood countries) are not a part of the negotiation process, the PA10 WG4 on Financing could be established as a platform to put forward recommendations of the EUSDR countries to the EC . | EUSDR countries’ position paper on 2014 – 2020 programming period | EUSDR stakeholders | End Jan. 2012 (NPC & PAC meeting) Mid 2013 | NOTE: Proposal not endorsed due to late stage of the negotiations.
Action ‘To Review Bottlenecks Relating to the Low Absorption of EU Funds
And to Ensure Better Coordination of Funding’

## Slide 15: Open questions
Decide on next steps
  Are the milestones feasible?
Open issues

## Slide 16: THANK YOU