## Slide 1: Results of the Working Group Meetings Civil Society (WG 2) & Regional Cooperation (WG 3)
2nd Steering Group Meeting
28th and 29th March 2012

## Slide 2: Content
Introduction
Objectives & methodological approach of the WGs
Roadmap for the Actions
Open questions

## Slide 3: 1. Introduction
EUSDR Governance structure
Coordination & Policy Level:
EC, High Level Group & Contact Points
„Rolling“ Action Plan
4 Pillars
11 Priority Areas
Actions
Projects
(as examples)
Steering Group
PDB
Project Leaders
Priority Area Coordinators
4 Working Groups

## Slide 4: 1. Introduction
SPECIFIC RESPONSIBILITIES OF THE WGs
Breaking down each action into further operational steps;
Identifying a certain numbers of demonstration projects not yet or already implemented which match the intention of the actions;
Propounding and identifying the opened issues/ questions which should be discussed on SG-level;
Meeting at least two times more within this year.
WGs AS THEMATIC PLATFORMS: projects or project ideas related to the Actions were discussed more into detail in order to address projects proposals from both the public and private sector

## Slide 5: 1. Introduction
EUSDR PA10 work structure
Priority Area 10: “stepping up institutional capacity and regional cooperation.”
Four working groups + special project:
1. WG1 - Institutional Capacity
2. WG2 - Regional Cooperation
3. WG3 - Civil Society
4. WG4 - Financing
5. Flagship project - Danube Implementation Facility
PA10: 8 actions

## Slide 6: 2. Objectives & methodological approach of the WGs
Input part
(prepared by PAC)
Working part
(WG Members and PAC)
RESULTS
(discussed in SG Meeting)

## Slide 7: 3. Roadmap for the Actions: Working Group 2
WORKING GROUP 2 (CIVIL SOCIETY) - OVERVIEW
3 actions allocated to the WG 2:
  Action 1: ‘To establish a Danube Civil Society Forum’,
  Action 2: ‘To ensure sufficient information flow and exchange at all levels’,
  Action 3: ‘To improve the trust of citizens and stakeholders in political authorities’.
certain number of demonstration projects allocated to each action
defined milestones allocated to each action
next steps, activities and tasks of the WG members to be done until next meeting

## Slide 8: 3. Roadmap for the Actions: Working Group 2
Milestone N°1 (operational steps) | Main Objective | Results | Responsibility | Deadline | Projects allocated to the Action
Elaborating a feasibility study prior to the establishment of the Danube Civil Society Forum | Identify the future common structure of the DCSF | Feasibility study | tbc | 12/ 2012 | Danube Civil Society Forum Danubiana – civil network development Femcities; Passing of Fire; Green Danube Networking etc.
Action 1: ‘To establish a Danube Civil Society Forum’

## Slide 9: 3. Roadmap for the Actions: Working Group 2
Milestone N°2 (operational steps) | Main Objective | Results | Responsibility | Deadline | Projects allocated to the Action
Building up an unique Youth Danube Education Exchange Network (YDEEN) | Create a platform for exchanging ideas and experiences from daily lives, culture and many other different issues when the students and scholars study abroad. | A project proposal is elaborated. | 3 WG members Mr Johann-Jakob Wulf, Chairmen of the Executive Board of Young Citizens Danube Network; Mr Lütgenau, President of the Danube Civil Society Forum; Gabor Tarr, Director of the Hungarian National Tourist Office) | 12/2012 | Danube Civil Society Forum Danubiana – civil network development Femcities; Passing of Fire; Green Danube Networking etc.
Action 1: ‘To establish a Danube Civil Society Forum’

## Slide 10: 3. Roadmap for the Actions: Working Group 2
Milestone N°3 (operational steps) | Main Objective | Results | Responsibility | Deadline | Projects allocated to the Action
Establishing an E-Government platform concerning the EUSDR’s issues | Enhance the position of CSOs to contribute to the implementation and decision-making-process Enhance the exchange of scientific know-how and good practices identified or developed | Virtual network which promotes the cooperation in urban revitalization, supports for modern urban technologies, housing projects and organize knowledge transfer, etc. | tbc | 12/2013 | Danube Civil Society Forum Danubiana – civil network development Femcities; Passing of Fire; Green Danube Networking etc.
Action 2: ‘To ensure sufficient information flow and exchange at all levels’

## Slide 11: 3. Roadmap for the Actions: Working Group 2
Milestone N°4 (operational steps) | Main Objective | Results | Responsibility | Deadline | Projects allocated to the Action
Making a wide public awareness campaign | Promote the EUSDR in short term and increase the Danube Region attractiveness in a long term | Cross-border / transnational promotion of the EUSDR Enhance the visibility of the EUSDR | tbc | 06/2013 | DRIBE CEEPUS Danube Region University for Public Governance Road Show on the Danube Strategy in Medium Cities EdTWIN CZ Etc.
Action 2: ‘To ensure sufficient information flow and exchange at all levels’

## Slide 12: 3. Roadmap for the Actions: Working Group 2
Milestone N°5 (operational steps) | Main Objective | Results | Responsibility | Deadline | Projects allocated to the Action
Building the TransCity Network for Public Relations for EUSDR Issues | Increased accessibility and use of data Improved government transparency and effectiveness Straightened trust of the citizens | Public relations activities | tbc | 06/2013 | DRIBE CEEPUS Danube Region University for Public Governance Road Show on the Danube Strategy in Medium Cities EdTWIN CZ Etc.
Action 3: ‘To improve the trust of citizens and stakeholders in political authorities’

## Slide 13: 3. Roadmap for the Actions: Working Group 3
WORKING GROUP 3 (REGIONAL COOPERATION) - OVERVIEW
3 actions allocated to the WG 3:
  Action 1: ‘To facilitate the administrative cooperation of communities living in border Regions’,
  Action 2: ‘To build Metropolitan Regions in the Danube Region’,
  Action 3: ‘To ensure sufficient information flow and exchange at all levels’.
certain number of demonstration projects allocated to each action
defined milestones allocated to each action
next steps, activities and tasks of the WG members to be done until next meeting

## Slide 14: 3. Roadmap for the Actions: Working Group 3
Milestone N°1 (operational steps) | Main Objective | Results | Responsibility | Deadline | Projects allocated to the Action
Definition of an efficient cross-border cooperation model on different levels | Overcome different systems making use of the existing European Grouping of Territorial Cooperation (EGTC) structure | Analysis on the effectiveness of EGTCs in the Danube Regions | tbc | 12/2012 | SECCo Common Strategy for the Sustainable Territorial Development of the Cross-border Area RO-BG EGTC “Ister-Granum Etc.
Action 1: ‘To facilitate the administrative cooperation of communities living in border regions’

## Slide 15: 3. Roadmap for the Actions: Working Group 3
Milestone N°2 (operational steps) | Main Objective | Results | Responsibility | Deadline | Projects allocated to the Action
Use the capacity of an existing Urban Network | Raise competiveness of the cities and regions in the Danube region and to enhance the benefit for lagging areas and capital cities | Regular network activities and information exchange | e.g. Council of Danube Cities and Regions (CoDCR) | 12/2012 (define stakeholders and develop concept for network activities) | Metropolitan Network Danube Region (MND) Network of associations of local authorities of South-East-Europe Danube metropolises – venue for SME and invertors’ encounters Etc.
  Action 2: ‘To build Metropolitan Regions in the Danube Region’

## Slide 16: Open questions