Please return the completed form by e-mail to Info@dsp.bwl.de

Please note: Fields with orange background will be filled in by the Danube Strategy Point!

| Basic Strategic Project (SP) Data |  |  |  |
| --- | --- | --- | --- |
| Full SP title: | START – Danube Region Project Fund |  |  |
| Short project title: (acronym) | START | Project logo: |  |
| Project website: | http://danube-capacitycooperation.eu/pages/start-overview | Project ID: | [PA1AXXX (e.g.: PA1A003] |
| Need and added value for EUSDR: | Project idea owners in the Danube Region are suffering from a lack of funding to initiate and to start the implementation of complex projects with strategic impact and to build up partnerships in a transnational environment. “Facilitation of project preparation” and “Small project support” were identified as major needs of project promoters. |  |  |
| Objective(s) of SP: | The Seed Money Facility START meets the identified needs with offering small scale funds for the preparation of transnational projects in the Danube Region and for the implementation of small projects with a transnational impact. |  |  |
| Planned SP activities: | The main activities of START are: - Organising the application procedure, incl. organisation and publication of the calls - Elaborating an assessment procedure, organisation and coordination of the Decision-making procedure - Concluding grant agreements with final beneficiaries of selected projects - Consultancy of selected project lead partners - Communication and information about the results of the calls, new rules, upcoming calls, etc. - Verification of project expenses, payments to beneficiaries and recovery - Progress and financial reporting to the European Commission - Submission of payment claims to the European Commission - Monitoring of the overall progress of the Fund |  |  |
| Deliverable(s) of SP: | - 2 Calls for proposals were organised: - 871 applications were received in the first call - 205 applications were received in the second call - 49 projects were selected for funding - 25 in the first call - 24 in the second call - The selected START projects address all Priority Areas |  |  |
| Macro-regional dimension: | - The project is implemented by the City of Vienna in cooperation with all PACs and their Steering Groups. - Partner Organisations from all Danube Region Countries are involved in the implementation of the selected projects |  |  |
| Transboundary impact: | The transboundary impact of START is guaranteed by supporting the preparation of transnational projects or the implementation of small projects with a transnational impact in the entire Danube Region. |  |  |

| Type, Status and Time Frame |  |  |  |  |
| --- | --- | --- | --- | --- |
| Type of SP: (please tick a box) | Single project Group of projects |  | Preparatory project Investment project x |  |
|  | Process |  |  |  |
| Current phase of SP1: (please tick a box) | Planning/preparatory phase Implementation phase x |  |  |  |
| Project start date: | 01.01.2014 | Project end date: |  | 31.12.2016 |
| Notes: | In 2014 the general structure of the project, the framework for the calls for proposals, the evaluation system and the selection procedure for the individual projects were established. 2 calls for proposals were launched, one in July 2014, one in May 2015, 49 START projects were selected for funding. The first projects started their implementation in March 2015 the last will be finalised by July 2016. At the current state (March 2016) midterm reports are check by the Implementing Body for projects of the 2nd call and final reports for the project of the 1st call. This includes also the verification of project expenses. The project is implemented according to the planned timeline. |  |  |  |

| Strategic Project Implementing Body |  |  |
| --- | --- | --- |
| Body: | PA 10 – City of Vienna Affiliated entity: EuroVienna - EU-consulting & -management GmbH |  |
| Contact person: | Name: | Rudolf Schicker |
|  | Organisation: | Priority Area Coordinator 10 - EUSDR (City of Vienna) |
|  | Address: | Kirchberggasse 33/35/Top 35 |
|  | Phone: | +43 (0)1 89 08 088 2201 |
|  | E-Mail: | rudolf.schicker@pa10-danube.eu |
|  | Website: | http://www.danube-capacitycooperation.eu/ |

| Strategic Project Team |  |  |
| --- | --- | --- |
| Project leader: | EuroVienna - EU-consulting & -management GmbH (affiliated entity to the City of Vienna) |  |
| Project partner(s): | Not applicable |  |
| Contact person from project leader’s team: | Name: | Gudrun Pabst |
|  | Organisation: | EuroVienna - EU-consulting & -management GmbH |
|  | Address: | Kaiserstraße 113-115 / 8 |
|  | Phone: | +43 1 89 08 088 2904 |
|  | E-Mail: | gudrun.pabst@eurovienna.at |
|  | Website: | http://www.eurovienna.at/ |

| Strategic Project Beneficiary |  |  |
| --- | --- | --- |
| Body: | Not applicable |  |
| Contact person: | Name: | Not applicable |
|  | Organisation: | Not applicable |
|  | Address: | Not applicable |
|  | Phone: | Not applicable |
|  | E-Mail: | Not applicable |
|  | Website: | Not applicable |

| Financing |  |  |  |  |
| --- | --- | --- | --- | --- |
| Approved: (please tick a box) | Yes Partly No x |  |  |  |
| Total budget of SP: | € 1,964.520,00 |  |  |  |
| Source(s) and amount (potential source(s) and amount(s) for SP in planning/ preparatory stage): (please tick a box and provide further info) | National/ regional funds: x | City of Vienna |  | € 98.226,00 |
|  | EU funds: x | DG Regio |  | € 1,866.294,00 |
|  | IFI loans: | [Name of source i.e. loans by IFIs, e.g. EIB, EBRD] |  | [Amount in EUR] |
|  | Private funds: | [Name of source] |  | [Amount in EUR] |
|  | Other: | [Name of source] |  | [Amount in EUR] |
| Notes: | [In case of partly approved financing for the SP, provide additional explanations and further information as relevant] [In case of SP with fully approved financing, provide as annex to the Project Data Sheet the approved financing plan(s) for each source] [In case of SP without approved financing, provide as annex to the Project Data Sheet the latest available financing plan(s) for each source] |  |  |  |

| EUSDR Compliance |  |
| --- | --- |
| Compliance with EUSDR Target: | DG Regional Policy commissioned a study on the need for financial instruments in the EU Strategy for the Danube Region (EUSDR) 2011. “Facilitation of project preparation” and “Small project support” were identified as major needs of project promoters. |
|  | START Danube Region Project Fund meets the identified needs with offering Seed Money for the preparation of transnational projects in the Danube Region and for the implementation of small projects with a transnational impact. |
| Compliance with EUSDR Action: | PA10 Action: “To review bottlenecks relating to the low absorption rate of EU funds and to ensure better coordination of funding”. |
|  | START supports the preparation of larger transnational projects in the Danube Region which aim at applying for EU funding. With the support of START partnerships are established, project concepts and budget plans are elaborated and project applications are submitted. |
| Relation to other EUSDR Target(s): | Targets from all PAs were addressed by START: - Only project proposals with relevance for the EUSDR and a specific Priority Area of the EUSDR were accepted - PACs and their Steering Groups themselves assessed the quality of the project proposals (this guarantees the relevance for the strategy and the respective PA) |
|  | Projects addressing targets from all PAs were supported by START. |
| Relation to other EUSDR Action(s): | Action from all PAs were addressed by START – see section above. |
|  | Projects addressing actions from all PAs were supported by START. |

| Other Relevant Issues |  |
| --- | --- |
| SP requirements: | - High commitment of START project partners to their project - Support from all PACs and their Steering Groups (mainly in the application and assessment phase) |
| Support for the SP: | All Danube Countries benefit from the initiative. |
| Follow-up project: | - A Seed Money Facility is planned in the scope of the Danube Transnational Programme. - A Danube Strategic Project Fund is planned |
| Any other issues: | The high numbers of applications received for START funding and the feedback from selected and rejected applicants reflect a high need for small scale funding in the Danube Region. |

| Links with other EUSDR Priority Areas |  |
| --- | --- |
| Relation to other Priority Areas of EUSDR: (please tick a box) | PA1a: To improve mobility and intermodality of inland waterways x PA1b: To improve mobility and multimodality – Road, rail and air links x PA02: To encourage more sustainable energy x PA03: To promote culture and tourism, people and people contacts x PA04: To restore and maintain the quality of waters x PA05: To manage environmental risks x PA06: To preserve biodiversity, landscapes and the quality of air and soils x PA07: To develop the knowledge society through research, education and information technologies x PA08: To support the competitiveness of enterprises, including cluster development : x PA09: To invest in people and skills x PA10: To step up institutional capacity and cooperation x PA11: To work together to promote security and tackle organised and serious crime x |
|  | Projects addressing targets and actions from all PAs were supported by START. |

| Meta Data |  |
| --- | --- |
| Dated created / by: | [DD.MM.YYYY / First and last name (organisation)] |
| Date of last update / by: | [DD.MM.YYYY / First and last name (organisation)] |

See concept paper for EUSDR Strategic project